# TOP 10 CRITICAL PROBLEMS

## Chicago Spending Without Active Contracts

At-Risk Amount: $68.9 Million
Total Requisitions: 1,112
Average Age: 189 Days

________________________________________________________________________________

Report Date: January 9, 2026
Data Source: Chicago Exhibit B Report

# 1. EXPIRED CONTRACTS - NEW CONTRACTS PENDING

$55.3M | 860 Requisitions | 80.4% of Total

Departments continue purchasing from vendors whose contracts expired

No legal protection, pricing agreements, or performance standards

FIX: 180-day pre-expiration renewal process + emergency bridge contracts

________________________________________________________________________________

# 2. WATER MANAGEMENT DEPARTMENT

$17.8M | 30 Requisitions | 25.9% of Total

Single largest department risk

$8M transaction with Badger Meter without contract

$5.2M in recurring chemical supplies (USALCO) without contract

FIX: Immediate review of $8M transaction + blanket POs for chemicals

________________________________________________________________________________

# 3. AVIATION DEPARTMENT

$11.8M | 80 Requisitions | 17.2% of Total

Safety-critical airport operations at risk

Industrial Fence Inc: 51 separate requisitions ($4M) without contract

Elevator maintenance ($3.6M) without active agreements

FIX: Emergency contract with Industrial Fence + multi-year facility contracts

________________________________________________________________________________

# 4. NO CONTRACTS AWARDED

$58M | 1,022 Requisitions | 91.9% of Total

92% of requisitions have NO contract in place yet

Only 78 out of 1,112 requisitions have contracts awarded

Severe bottleneck in contract award process

FIX: Add procurement staff + 120-day award targets + monthly reporting

________________________________________________________________________________

# 5. HIGH-VALUE TRANSACTIONS (>$500K)

$40.9M | 36 Transactions | 59% of Total Spend

Major purchases proceeding without contracts:

$8.0M - Badger Meter (water meters)

$4.3M - AT&T (telecom)

$1.9M - Computer Aid (IT services)

$1.9M - CASCADE Engineering (environmental)

FIX: Hard stop in system for purchases >$500K without contract

________________________________________________________________________________

# 6. PARTS & SUPPLIES CATEGORY

$17.4M | 171 Requisitions | 25.2% of Total

Largest spending category without contracts

Essential recurring needs (cannot stop purchasing)

Water Management: $10.4M in parts alone

FIX: Category management + blanket POs + pre-approved catalogs

________________________________________________________________________________

# 7. FLEET & FACILITY MANAGEMENT

$10.7M | 566 Requisitions | 50.9% of All Requisitions

Highest volume department (566 of 1,112 requisitions)

Multiple vendors with 30-75 separate requisitions each:

Arlington Glass & Mirror: 75 requisitions

Bluetriton Brands: 60 requisitions

Parkway Elevators: 43 requisitions

Small transactions averaging only $18,865

FIX: Vendor consolidation + blanket POs + corporate credit cards for <$5K

________________________________________________________________________________

# 8. VENDOR CONCENTRATION RISK

Top 20 Vendors = $48.7M (70.7% of Total)

Heavy reliance on vendors without contracts

Chronic Repeat Offenders:

Industrial Fence Inc: 51 requisitions ($4.0M)

Arlington Glass & Mirror: 75 requisitions ($475K)

Bluetriton Brands: 60 requisitions ($75K)

Vendors can discontinue service at any time

FIX: Master agreements with top 5 vendors within 30 days

________________________________________________________________________________

# 9. AGING REQUISITIONS

Average: 189 Days | Oldest: 371 Days (Over 1 Year)

January 2025 requisitions still pending (371 days old): $8.6M

March 2025 requisitions (305 days old): $10.5M

September 2025 requisitions (120 days old): $10.7M

Systemic delays in procurement process

FIX: 90-day resolution target + dedicated staff for aged backlog >180 days

________________________________________________________________________________

# 10. PROCUREMENT PROCESS BOTTLENECKS

Key Stuck Points:

Solicitation Response Evaluation: $8.4M stuck

City Law Department Review: $7.4M delayed

Various process phases with major delays

FIX: Process mapping + add legal staff + 120-day time limits + fast-track for routine purchases

________________________________________________________________________________

# IMMEDIATE ACTION PLAN

## WITHIN 30 DAYS:

Award emergency contracts to top 5 vendors

CFO review of all 36 transactions over $500K

Assign staff to 371 requisitions pending >180 days

Implement system hard stop for >$500K purchases without contract

## WITHIN 90 DAYS:

Intensive support for Water Management, Aviation, Fleet/Facility departments

Establish blanket POs for Parts & Supplies

Reduce repeat small-transaction vendors by 50%

Implement 90-day contract expiration alerts

## WITHIN 180 DAYS:

Update procurement policies to prevent expired contracts

Implement automated contract tracking system

Add procurement staff to eliminate backlog

Monthly compliance reporting to City Council

________________________________________________________________________________

# RISK ASSESSMENT

| Risk Type | Level | Impact |
| --- | --- | --- |
| Legal | HIGH | $68.9M without contractual protection |
| Financial | HIGH | No price protection or competitive bidding |
| Operational | CRITICAL | Vendors can stop service at any time |
| Audit | CRITICAL | Non-compliance with procurement regulations |
| Reputational | HIGH | Public perception of poor controls |

________________________________________________________________________________

# BOTTOM LINE

The City of Chicago has nearly $69 million in unprotected spending. The top 3 departments (Water Management, Aviation, Fleet/Facility) account for $40.3M (58.6%) of the risk. Expired contracts with pending renewals account for $55.3M (80.4%). Only 7% of requisitions have contracts actually awarded.

Immediate action required on top 10 vendors and all transactions over $500K.

________________________________________________________________________________

Document Prepared: January 9, 2026
Data Source: Chicago Exhibit B Report - Custom_Exhibit-B_Report (6).xlsx
Analysis Tool: Claude Code AI